|  |  |
| --- | --- |
| Northeast Roundtable Date: | January 22, 2020  |
| Update Prepared By: | Tara Forest |
| Updated Presented to Roundtable by: | Dale Morgan |

**PROJECT OVERVIEW**

|  |  |
| --- | --- |
| Project Contact  | Dale Morgan, Tara Forest  |
| Ministry/Agency | Ministry of Indigenous Relations and Reconciliation  |
| Description  | The Province of BC is settling an outstanding claim for reserve land with five Treaty 8 First Nations. This project involves the transfer of lands to Treaty 8 First Nations. |
| Project Phases and Schedule  | Land selection identification (complete)Status and Research of Selections (in progress)* Includes stakeholder, tenure holder and public engagement
* May include signing of the Settlement and Lands Agreement that set out the land transfer process

Agreement on Final Selection Lands and Approval to Transfer SurveyLegal/Administrative Interests ResolutionTransfer of Land to Federal Reserve or Fee Simple |
| Project Information Links | * GovTogether: <https://engage.gov.bc.ca/govtogetherbc/consultation/land-transfers-in-northeast-british-columbia/>
	+ Links to maps and other information about TLE land transfers
	+ Opportunity to provide feedback
 |

**PROJECT UPDATE DETAILS**

|  |  |
| --- | --- |
| Update Highlights  | * The Province continues to work on the Settlement and Lands Agreements
* Settlement and Lands Agreement update:
	+ Work is ongoing between BC, First Nations and Canada
* Saulteau Update:
	+ Saulteau’s parcels are being presented today
	+ First Nations consultation has been initiated
	+ Stakeholder engagement has been initiated
* Blueberry Update
	+ Red Creek:
		- *Land Act* s.17 has been approved and reasons for decisions posted
		- Engagement with stakeholders is on-going
		- Open House planned for February 12th
	+ Charlie Lake:
		- *Land Act* s.16 has been approved and reasons for decisions posted
		- Engagement with stakeholders is on-going
		- Open House planned for February 5th
	+ Pink Mountain
		- Working closely with Rec Sites and Trails from FLNRO and Blueberry River First Nations to identify a workable route
* West Moberly Update
	+ First Nations consultation is on-going
	+ Stakeholder engagement is on-going
* Halfway Update
	+ Agency review process complete
	+ Stakeholder Engagement wrapping up
	+ First Nation consultation on-going
* Doig Update
	+ Detailed agency review process starting
	+ First Nation consultation is complete
	+ Stakeholder Engagement on-going
 |
| Key Dates  | * Open Houses February 5th and 12th
* Next Roundtable meeting
 |
| Meeting Reference Materials | * N/A
 |

**STATUS REPORT ON ACTION ITEMS (only outstanding actions listed here)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date Assigned** | **Item for Follow Up / Action** | **Assigned To** | **Status Update**  |
| Date of NER meeting  | Action item | Person  | Status of action  |
|  | Define Access types, how they are defined in various legislation, and approach in negotiations. | Tara | In progress |
|  | Confirm how current taxation regime will be impacted by TLE and ATR. Assess tax implications for local governments (e.g. taxable infrastructure removed from tax base when transferred to Federal Reserve) | Tara | In progress |
|  | Develop a Fact Sheet and Q&A in response to questions raised at open house meetings | Tara | In progress (at approvals stage) |
|  | Ask ADM/Minister to confirm how much money the Federal government has provided to the Province to support the TLE land transfer process. | Dale | Open |
|  | Confirm how the TLE money transferred from Canada to BC will be used/allocated. | Dale | Open |